## Sketch
Waddell TR 3 #3813 | Waddell TR 3 #3813 | [9 empty] | Savanna #417
Drilling Prognosis for Savanna #417
[11 empty] | SHL Inputs |  | BHL | NOTES:
|  | Surface: | 2010' FSL, 650' FWL |  |  |  |  | AFE # | CX3818 |  | 2010 | S |  | Need to decide on motor
|  | Bottom: | 2010' FSL, 650' FWL |  |  |  |  | Well ID # | 669 |  | 650 | W |  | Do we need to take surface to GAU depth if we are setting intermediate?
|  |  | Sec 22, Blk B-25 |  |  |  |  | Permit # | 868552 |  | 22 | Sec |  | Will need to move 13-3/8" BOP system off #415 to location
|  |  | PSL |  |  |  |  | API # | 42-103-36784 |  | B-25 | Blk |  | Savanna to provide 4-1/2" DS-40 drill pipe
|  | LAT/LON (NAD83): | 31.546657, -102.490691 |  |  |  |  | Elevation | GL 2765', KB 2777' (12' AGL) |  | 2765 | GL
|  | LAT/LON (NAD27): | 31.546521, -102.490269 |  |  |  |  | Lease: | Waddell TR 3 |  | 850 | WTR
|  | County: | Crane |  |  |  |  | Field: | University Waddell (Devonian)
|  | Geology | Casing & Cement |  |  | Wellhead |  | General Notes
| TVD | Formation |  |  | GE API Head |  |  | Notify RRC prior to spud
-50 | [5 empty] | 17-1/2" |  | & prior to running & cementing all casing strings
100
250 | Near Surface | Red Beds | [5 empty] | Drill out with 8.6 ppg FW, vis 33-36, pH > 9.0, no WL control
400 |  |  | Lead: 300 sx 12.8ppg Class C
550 |  |  | Top of Lead @ 0' |  |  |  |  | WL Totco Inc Survey every 500'
700 |  |  | Lead Excess@ 30%
850
1000 | [7 empty] | Pump 2 sacks paper & 1/2 soap stick every 100' drilled
1150 |  |  | Tail: 250 sx 13.8ppg Class C |  |  |  |  | Pump ~10 bbl high visc sweeps from slug pit every 100'-200'
1300 |  |  | Top of Tail @ 600'
1450 |  |  | Tail Excess@ 86% |  |  |  |  | Add 20sx of starch 300' from TD & circulate through steel pits as needed
1600 | [7 empty] | Pump the rest of the high visc pill when on bottom |  |  | Thickness
1750 |  | Rustler | [8 empty] | Rustler |  | 0
1900 |  | Anhydrite | 13-3/8" 48# H-40 STC |  |  | 900 |  | Test Casing to 1,000 psi
|  |  | No deeper than 1050' per TCEQ |  |  | 11" |  | RU H2S package
2020 |  | Salado Salts | [5 empty] | RU mud loggers at start of Intermediate hole |  |  | Salado Salts |  | 0
2200 |  | Salts
2380 |  |  | Lead: 500 sx 11.6ppg Class C |  |  |  |  | Drill out with 10.0 ppg Brine, vis 28-32, pH 10, no WL control
2560 |  |  | Top of Lead @ 0' |  |  |  |  | Refer to mud properties table
2740 | 2278.7 | ~ Yates | Lead Excess@ 84% | [7 empty] | 0 |  | 0
2920 |  | Sands | [5 empty] | Survey every 200' in the Salts 650' - 2600'
3100 |  |  | Tail: 400 sx 14.4ppg Class H | [7 empty] | 0 |  | 3515.8
3280 |  |  | Top of Tail @ 3000'
3460 | 3056.3 | ~Queen | Tail Excess@ 103% | [7 empty] | Queen |  | -3515.8
3640
3820
4000 | [7 empty] | Add 20sx of starch 300' from TD & circulate through steel pits as needed |  |  | 0 |  | 5042.7
4180 | 3515.8 | ~ San Andres | [5 empty] | Pump the rest of the high visc pill when on bottom
4360 |  | Dolomite | [7 empty] | 0 | Upper Clearfork |  | 4957.3
4540
4720
4900 |  |  | 8-5/8" 32# J-55 LTC |  |  | 4000 |  | Test Casing to 1500psi
5080 | 4550.2 | Glorietta |  |  |  | 6-3/4"
5260 |  | Sands | [5 empty] | Drill out with 10.0 ppg Brine, vis 28-32, pH 10, no WL control
5440 | 5042.7 | Upper Clearfork | [5 empty] | Refer to mud properties table
5620 |  | Dolomite | Lead: 500 sx 11.6ppg Class C
5800 |  |  | Top of Lead @ 0'
5980 | 5362.3 | Tubb | Lead Excess@ 60% |  |  |  |  | Continue 2-man mud logging over shakers
6160 |  | Sands | [5 empty] | after drilling out of Intermediate casing
6340 |  |  | Tail: 850 sx 14.4ppg Class H
6520 | 6047.3 | Wichita Albany | Top of Tail @ 5000' |  |  |  |  | Contact Engineer before any trips
6700 |  |  | Tail Excess@ 23% |  |  |  |  | Keep hole full during trips
6880 | 7053 | Wolfcamp
7060 |  |  | Marker Joint @ 6,500' and 8,500' MD |  |  |  |  | Add 30 sx starch @ 300' from TD & circulate through steel pits
7240 | 9119 | Devonian | [5 empty] | <20cc WL, vis 30-32
7420
7600 | 10000 | TVD | 5-1/2" 20# L-80 LTC (w/ TDC) |  |  | 10000
Approvals
| Prepared by: | [5 empty] | Reviewed by:
|  | Kevin Foro, Asset Engineer |  | Date |  |  |  | Ian Smith, Permian VP |  | Date

## Sketch_final (hidden)
Waddell TR 3 #3813
Drilling Recap
|  | Surface: | 2010' FSL, 650' FWL |  |  | AFE # | #REF!
|  | Bottom: | 2010' FSL, 650' FWL |  |  | XTO ID # | 42-103-36784
|  |  | Sec 22, Blk B-25 |  |  | Permit # | CX3818
|  |  | PSL |  |  | API # | #REF!
|  | County: | 31.546521, -102.490269 |  |  | Elevation | GL 2765', KB 2777' (12' AGL)
|  | Field: | Crane |  |  | Lease: | Waddell TR 3
|  | Well Plan: | #REF!
|  | Geology | Casing & Cement |  | Wellhead | General Notes | [6 empty] | TOC | TOC | Est Circ | Est Circ | Col ht | Desired | Desired |  | Vol | Vol
[9 empty] | Vol | Yield | Est Losses | Slurry | w/loss | no loss | w/loss | no loss | w/loss | Excess | TD | Yield | w/ex | no ex | Theoretical Ex | Circ vol | Act Loss
|  |  |  | GE API Head |  |  |  | Surf Cement | sx | cuft/sx | % | bbl | ft | ft | sx | sx | ft | % | ft | cuft/sx | sx | sx | % | sx | %
| TVD | Formation |  |  | 17-1/2" | Conductor (not shown): |  | Lead | 300 | 1.85 | 225.2% | 98.8455 | 0 | 0 | 114 | 392.5372 | 416.1941 | 150% | 0 | 1.85 | 137.4211 | 54.9684 | 445.8% | 114 | 225.2%
100 | [5 empty] | 16" hole to 53', 14" 40# Construction (B) csg, cmt w/13 sx to surf |  | Tail | 250 | 1.6 | 225.2% | 71.24 | 416.1941 | -673.3842 |  |  | 483.8059 | 150% | 400 | 1.6 | 198.6165 | 79.4466 | 214.7%
200 | Near Surface | Red Beds | Lead: 300 sx 12.8ppg Class C |  |  |  |  | Total | 550 |  |  | 170.0855 | [8 empty] | 336.0376 | 134.415 | 309.2%
300 |  |  | #REF! |  |  | Surface Wellhead:
1000 |  |  | Top of Lead @ 0' |  |  | GE A Section casing head, 8-5/8" SOW x 11" 3M (test 1000 psig) |  |  | ID | OD | Depth | ID Cap | OD Cap | Ann Cap
1100 |  |  | Circ 114 Sx, (calc 126% loss) |  |  |  |  | Surface | in | in | ft | bbl/ft | bbl/ft | bbl/ft
1200 | [5 empty] | Surf Bit / BHA: |  | Surf Hole | 11 |  | 900 | 0.11754
1300 |  |  | 0 |  |  | GT65DM PDC bit ( jets) |  | Surf Csg in OH | 8.097 | 8.625 | 900 | 0.063689 | 0.072266 | 0.045278
1400 |  |  | Tail: 250 sx 13.8ppg Class C |  |  | Bit > Bit sub & float > 2 x 8"DC > XO > 10 x 6-1/2" DC > 10 x 4-1/2" HWDP
1500 |  |  | 1160 | [5 empty] | Surface casing volume: | 57.3201 | bbl
1600 | [5 empty] | Surface Hole Comments |  |  | Surface annular volume: | 40.7504 | bbl
1700 | [5 empty] | - Washed down last jt of casing - Floats held, tag @ 1885'
1800 |  | Rustler | [10 empty] | TOC | TOC | Est Circ | Est Circ | Col ht | Desired | Desired |  | Vol | Vol
1900 |  | Anhydrite | 13-3/8" 48# H-40 STC |  | 900 |  |  |  | Vol | Yield | Est Losses | Slurry | w/loss | no loss | w/loss | no loss | w/loss | Excess | TD | Yield | w/ex | no ex | Theoretical Ex | Circ vol | Act Loss
2000 |  |  | No deeper than 1050' per TCEQ |  | 11" | Production Wellhead: |  | Prod Cement | sx | cuft/sx | % | bbl | ft | ft | sx | sx | ft | % | ft | cuft/sx | sx | sx | % | sx | %
2100 |  | Salado Salts |  |  |  | GE B Section tubing head, 11" 3M x 7-1/16" 5M (test 2400 psig) |  | Lead | 500 | 2.82 | 29.37% | 251.121 | 0 | 0 | 44.3653 | 244.9377 | 5156.7593 | 150% | 0 | 2.82 | 887.8942 | 355.1577 | 40.78% | 86 | 29.37%
2200 |  | Salts | [5 empty] | Tail | 850 | 1.29 | 29.37% | 195.2867 | 5156.7593 | 3734.4656 |  |  | 4843.2407 | 150% | 5200 | 1.29 | 1611.7618 | 644.7047 | 31.84%
3600 |  |  | Lead: 500 sx 11.6ppg Class C |  |  | Bit / BHA: |  | Total | 1350 |  |  | 446.4076 | [8 empty] | 2499.656 | 999.8624 | 35.02%
|  |  | Lead: 500 sx 11.6ppg Class C |  |  | GT65WRK PDC bit (1.035 jets)
3700 |  |  | Top of Lead @ 0' |  |  | Bit > Motor w/float > Monel w/ MWD survey tool > XO >6-1/2" STAB > 1 x 4-1/2" DC > 6-1/2" STAB > 31 x 4-1/2" HWDP > 4-1/2" 16.6# G-105 EU DP |  |  | ID | OD | Depth | ID Cap | OD Cap | Ann Cap
3800 |  | #REF! | Circ 86 Sx, (calc 91% loss) |  |  |  |  | Production | in | in | ft | bbl/ft | bbl/ft | bbl/ft
3900 |  | #REF! | Tail: 400 sx 14.4ppg Class H |  |  |  |  | Prod Hole | 7.875 |  | 10000 | 0.060244
4000 | #REF! | #REF! | Top of Tail @ 3000' |  |  | Max DLS: 0.28 deg / 100' @ 5087' MD |  | Prod Csg in Surf | 4.892 | 5.5 | 900 | 0.023248 | 0.029386 | 0.034303 |  |  |  | fix Est Circ & Vol w/ex
4100 | #REF! |  | Tail Excess@ 103% |  |  | Max inc: 2 deg @ 1241' |  | Prod Csg in OH | 4.892 | 5.5 | 10000 | 0.023248 | 0.029386 | 0.030858
4200 | #REF! | Sands
5700 |  | Tubb |  |  |  | Logging: tag @ 5098' |  |  | Prod casing volume: | 232.4817 | bbl
5800 | 5362.3 | Sands |  |  |  | Schlumberger Triple-Combo |  |  | Prod annular vol to shoe: | 280.8113 | bbl
5900 | #REF! | #REF! | [6 empty] | Prod annular vol shoe to surf: | 30.8726 | bbl
6000 |  | #REF! | Marker Joint @ 3979' (22') |  |  | Production Hole / Overall Comments: |  |  | Prod annular vol total: | 311.6839 | bbl
6100 | #REF! | #REF! |  |  |  | - - DT (total XX hrs, does not count bad weather contributing to slower speeds): 0.5 hrs rig repair (Norton), 4 hrs stuck Totco, 0.5 hrs rig pump repair (Norton), 1 hr replace ring gasket (Norton), 8 hrs plugged DP
6200 | #REF! | #REF!
6300
6400 | #REF! | #REF!
6500 |  | #REF!
6600 | 5042.7 | Upper Clearfork
6700
| 6047.3 | Wichita Albany
6800 |  |  | #REF!
| 7053 | Wolfcamp | Tail: 850 sx 14.4ppg Class H
6900 | #REF! | #REF! | Top Tail @ 3610'
7000 | #REF! | #REF!
| 9119 | Devonian
est PBTD @ 5050'
| #REF! | #REF!
| #REF! | #REF! | 5054
| #REF! | #REF!
7100 | 10000 | TVD | 5-1/2" 20# L-80 LTC (w/ TDC) |  | 10000
Drilling Results
|  | Spud Date: |  |  |  | Avg Well ROP (ft / hr): | 87.0345
|  | Rig Release Date: |  |  |  | Total Drilling Time (hr): | 58
|  | Total Drilling Days: | 0 |  |  | Avg Drill Time (ft / day): | #DIV/0!
|  | 11" Surf BHA |  |  |  | 7-7/8" Production BHA
|  | Depth Drilled (ft): | 1832 |  |  | Depth Drilled (ft): | 3216
|  | Avg ROP (ft/hr): | 114.5 |  |  | Avg ROP (ft/hr): | 76.6
|  | Drill Time (hr): | 16 |  |  | Drill Time (hr): | 42
|  | WOB Min / Max (klbf) | 20 / 20 |  |  | WOB Min / Max (klbf) | 10 / 30
|  | RPM Min / Max (rpm): | 100 / 100 |  |  | RPM Min / Max (rpm): | 75 / 105

## Tech Data
Waddell TR 3 #3813 Technical Data
Mud Properties
Hole Size |  | Mud Type |  |  | Weight (ppg) |  | Funnel Visc (s/qt) |  | PV | YP | FL | pH |  | Pm | MBT | %LGS
17-1/2" |  | FW / Gel / Lime |  |  | 8.3 - 8.7 |  | 33-36 |  | 2-6 | 2-6 | NC | 9.0-10 |  | 1 | - | < 6
17-1/2" (300' F/TD) |  | FW / Gel / Lime / Starch |  |  | 8.3 - 8.7 |  | 33-36 |  | 2-6 | 2-6 | <10 cc | 9.0-10 |  | 1 | - | < 6
11" |  | Brine / Salt Gel / Lime |  |  | 10.0-10.2 |  | 28-32 |  | 1-3 | 1-3 | NC | 10 |  | - | - | < 2
11" (300' F/TD) |  | Brine / Salt Gel / Lime / Starch |  |  | 10.0-10.2 |  | 30-32 |  |  | 1-3 | <20 cc | 10 |  | - | - | < 2
6-3/4" |  | Brine / Salt Gel / Lime |  |  | 10.0-10.2 |  | 28-32 |  | 1-3 | 1-3 | NC | 10 |  | - | - | < 2
6-3/4" (300' F/TD) |  | Brine / Salt Gel / Lime / Starch |  |  | 10.0-10.2 |  | 30-32 |  |  | 1-3 | <20 cc | 10 |  | - | - | < 2
Bit & BHA Information
Hole Size | Bit Type | Vendor | Model |  | Jets | TFA (in2) | ROP Target | BHA
17-1/2" | PDC | Halliburton | GT65DM |  | 3x22s |  | See Parameter | Bit > Bit sub & float > 2 x 8"DC > XO > 10 x 6-1/2" DC > 10 x 4-1/2" HWDP
11" | PDC | Halliburton | GT65DMHEO |  | 6x15s | 1.035 | See Parameter | Bit > Motor w/float > Monel w/ MWD survey tool > XO > 12-1/4" STAB > 1 x 8" DC > 12-1/4" STAB > 2 x 8" DC > 10 x 6-1/2" DCs > 10 x 4-1/2" HWDP > 4-1/2" 16.6# G-105 EU DP
6-3/4" | PDC | Halliburton | GT65WRK |  | 6x15s | 1.035 | See Parameter | Bit > Motor w/float > Monel w/ MWD survey tool > XO >6-1/2" STAB > 1 x 4-1/2" DC > 6-1/2" STAB > 31 x 4-1/2" HWDP > 4-1/2" 16.6# G-105 EU DP
**Check with Engr to confirm bit vendor ** All parameters are recommended not hard limits
Motor Specs
Size | Stages |  | Vendor | Speed Ratio |  | Flow Range |  | Speed Range |  | Max Diff Press |  | Max Torque |  | Bit to Bend
8" | 7/8 |  | Baker | 0.15 rev / gal |  | 395 - 900 gpm |  | 60-135 rpm |  | 1150 |  | 13500 |  | 1.83
5-1/8" | 5/6 6.5 |  | Baker | 0.51 rev / gal |  | 106-360 gpm |  | 55-185 rpm |  | 1340 |  | 5100 |  | 1.8
Casing Data
Interval | Size (in) | Grade | Weight (ppf) | Thread | ID (in) | Drift (in) | Cap (bbl / ft) | Collapse (psi) |  | Burst (psi) |  | Tension (1000 lb) |  | Make-up (ft-lb)
[8 empty] | Rated | 80% | Rated | 80% | Rated | 80% | Min | Opt | Max
Surface | 13-3/8 | H-40 | 48 | STC | 12.715 | 12.559 | 0.157 | 770 | 616 | 1730 | 1384 | 541 | 432 |  |  |  |  | #DIV/0! | #DIV/0!
Int | 8-5/8 | J-55 | 32 | LTC | 7.921 | 7.796 | 0.0609 | 2530 | 2024 | 3930 | 3144 | 417 | 333
Prod | 5-1/2 | L-80 | 20 | LTC | 4.778 | 4.653 | 0.0222 | 8830 | 7064 | 9190 | 7352 | 416 | 332 | 1850 | 2470 | 3090 |  | 25.1% | 25.1%
Centralizer Program
Casing String |  | Interval |  |  | Spacing |  |  | Est Joint Count |  |  | Est Turbolizers |  |  | Est Centralizers
13-3/8" |  | 1st and 2nd joints |  |  | 1 per joint |  |  | 2 |  |  | 0 |  |  | 2
13-3/8" |  | Thereafter to surface |  |  | 1 every 4th collar |  |  | 20 |  |  | 0 |  |  | 5
13-3/8" - Total | [7 empty] | 22 |  |  | 0 |  |  | 7
8-5/8" |  | 1st and 2nd joints |  |  | 1 per joint |  |  | 2 |  |  | 0 |  |  | 2
8-5/8" |  | 3rd jnt to top of San Andres |  |  | 1 per 2 jts |  |  | 9 |  |  | 0 |  |  | 5
8-5/8" |  | San Andres - Surf |  |  | 1 per 6 jts |  |  | 83 |  |  | 0 |  |  | 14
8-5/8" Total | [7 empty] | 94 |  |  | 0 |  |  | 21 | [7 empty] | 0.045278 | bbl/ft
5-1/2" |  | 1st and 2nd joints |  |  | 1 per joint |  |  | 2 |  |  | 0 |  |  | 2 | [7 empty] | 0.030858 | bbl/ft |  |  | 1.4673
5-1/2" |  | 3rd jnt to 100' above Int shoe |  |  | 1 every 3rd collar |  |  | 142 |  |  | 0 |  |  | 48
5-1/2" |  | therafter to surface |  |  | 1 every 6th collar |  |  | 92 |  |  | 0 |  |  | 16
5-1/2" - Total | [7 empty] | 236 |  |  | 0 |  |  | 66
Cement Program
Casing | Slurry | Volume (sx) | Cement | [9 empty] | Weight (ppg) | Yield (ft3/sk) | Water (gal/sk) | Volume (bbls) | Gauge (bbls) | OH Excess | Quoted Price | CMT Tops |  |  |  | OH Excess calculation (Int-lead)
13-3/8" | Lead | 300 | Class C | [9 empty] | 12.8 | 1.85 | 9.77 | 98.8455 | 74.2332 | 33.16% |  | Lead | Tail |  |  | Casing | 76.3091 |  | 174.8119
13-3/8" | Tail | 250 | Class C | [9 empty] | 13.8 | 1.6 | 7.88 | 71.24 | 37.1166 | 85.2% |  | 0 | 600 |  |  | OH | 95.0842 |  | 83.8496
8-5/8" | Lead | 500 | Class C | [9 empty] | 11.6 | 2.82 | 16.4 | 251.121 | 171.3933 | 83.85% |  | Lead | Tail |  |  |  |  | OH Excess Calculation (Prod-tail)
8-5/8" | Tail | 400 | Class H | [9 empty] | 14.4 | 1.29 | 5.7 | 91.8996 | 45.2782 | 103% |  | 0 | 3000 | 500' Above Sand Andres |  |  |  | Casing | -31.5643 | 226.8509
5-1/2" | Lead | 500 | Class C | [9 empty] | 11.6 | 2.82 | 16.4 | 251.121 | 157.8213 | 59.12% |  | Lead | Tail | Lead in Casing only no open hole |  |  |  | OH | 185.1503 | 22.5225
5-1/2" | Tail | 850 | Class H | [9 empty] | 14.4 | 1.29 | 5.7 | 195.2867 | 153.5861 | 22.52% |  | 0 | 5000 | ~100' above uppermost injection perforations
Logging Program
Depth |  |  | Mudloggers | [6 empty] | Comments
N/A
Depth |  |  | Logs | [6 empty] | Comments
TD to Surface Csg |  |  | Triple Combo / Spectral GR | [6 empty] | Repeat Pass fr/ bottom - 250'
Surface Csg to Surface |  |  | GR / Neutron | [6 empty] | Record & Display: Limestone matrix, neutron-density cross-plot porosity data
Wellhead Information
Section |  |  |  |  | Bottom |  |  |  | Top |  |  |  | Slips
A - Section (CSGHD) |  |  |  |  | 13-3/8" SOW |  |  |  | 13-5/8" 3M Flange |  |  |  | 13-3/8"
B - Section (TBG SPOOL) |  |  |  |  | 13-5/8" 3M |  |  |  | 11" 3M |  |  |  | 8-5/8"
C - Section (TBGHD) |  |  |  |  | 11" 3M Flange |  |  |  | 7-1/16 5M |  |  |  | 5-1/2"
Notable changes
Savanna to provide 4-1/2" DS-40 drill pipe. Nominal I.D. = 3.826". Nominal weight = 16.6 lb/ft.
Source 13-3/8" BOP stack & rotating head from Savanna #415

## Interval Specific Parameter
Waddell TR 3 #3813 Interval Specific Parameter Map
17-1/2" Surface (GT65DM )
Start | End | ROP Target | WOB Min | WOB Max | WOB Target | Rotary Min | Rotary Max | Rotary Target | GPM Min | GPM Max | GPM Target | Motor Diff | Total RPM | Interval Notes
0-500' | Surf | Max | 10 | 30 | 20 | 85 | 120 | 110 | 400 | 500 | 500 | NA | 110 | Reach targets as soon as 8" collars clear conductor.
500-900' | Red Beds | Max | 25 | 40 | 35 | 105 | 150 | 130 | 400 | 500 | 500 | NA | 130
11" Intermediate (GT65DMHEO )
Depths | Zone | ROP Target | WOB Min | WOB Max | WOB Target | Rotary Min | Rotary Max | Rotary Target | GPM Min | GPM Max | GPM Target | Motor Diff Target | Total RPM (.21rev/gal) | DOC | Interval Notes |  | DOC | 0.28
900-2278.7' | Rustler-Yates |  | 30 | 45 | 35 | 50 | 70 | 65 | 450 | 550 | 550 | 400+ | 180 | 0 | Salado Salt formation, ensure to drill out with 10 ppg Brine. |  | 0
2228.7-2328.7' | Yates Deviation Zone | 150 | 35 | 45 | 40 | 65 |  |  | 450 | 550 | 500 | 400+ | 170 | 0.17647 | Deviations seen in the salts, especially around 2,400'. Focus on WOB and RPM parameters
2328.7'-3465' | Yates-San Andres |  | 35 | 45 | 40 | 60 | 80 | 65 | 450 | 550 | 500 | 400+ | 170 | 0 |  |  | 0
| Transition into Grayburg | 90 |  |  | N/A | 55 |  |  | 450 | 550 | 450 | N/A | 180 | 0.1 | Transition 50' before to 50' past Grayburg. Set ROP Target and Rotary Target through transition with WOB MAX limit set at 40K for stack out safety purpose. |  | 0.1
| Grayburg - San Andres Transition |  | 25 | 35 | 25-28 | 45 | 85 | 70 | 450 | 550 | 490 | 400+ | 205 | 0 | Water flows possible, can have high H2S concentrations. |  | 0
3465'-3565' | Transition into San Andres | 90 | 30 | 45 | 40 | 55 |  |  | 450 | 550 | 500 | 500+ | 160 | 0.1125 | Transition 50' before to 50' past San Andres. Focus on WOB and RPM parameters |  | 0.1125
#NUM! | San Andres - Glorieta |  | 30 | 45 | 40 | 50 | 60 | 55 | 450 | 550 | 500 | 500+ | 160 | 0 | Once San Andres is reached by verification of cuttings, continue to regular drilling. |  | 0
#NUM! | Transition into Glorieta | 90 | 30 | 45 | 40 | 55 |  |  | 450 | 550 | 500 | 500+ | 160 | 0.1125 | Transition 50' before to 50' past Glorieta. Focus on WOB and RPM parameters |  | 0.1125
50-4995' | Glorieta - Upper Clearfork |  | 30 | 45 | 40 | 50 | 60 | 55 | 450 | 550 | 500 | 400+ | 160 | 0 |  |  | 0
6-3/4" Production (GT65WRK )
4995-5095' | Transition into Upper Clearfork | 90 | 30 | 40 | 35 | 55 |  |  | 450 | 550 | 500 | 500+ | 105 |  | Transition 50' before to 50' past Upper Clearfork. Focus on WOB and RPM parameters |  | 0.17143
5095-5310' | Upper Clearfork - Tubb |  | 30 | 40 | 35 | 60 | 70 | 65 | 450 | 550 | 500 | 500+ | 170 |  |  |  | 0
5310-5410' | Transition into Tubb | 85 | 30 | 40 | 35 | 55 |  |  | 450 | 550 | 500 | 500+ | 160 | 0.10625 | Transition 50' before to 50' past Tubb. Focus on WOB and RPM parameters
5410-5420' | Tubb - Lower Clearfork |  | 30 | 40 | 35 | 60 | 70 | 65 | 450 | 550 | 500 | 400+ | 170 | 0 | High WOB and Low RPMS will keep bit engaged in ratty formation
5470-7005' | Lower Clearfork - Wichita Albany |  | 30 | 40 | 35 | 60 | 70 | 65 | 450 | 550 | 500 | 500+ | 170 |  | Severe losses are possible
7005-7105' | Transition into Wolfcamp | 85 | 30 | 40 | 35 | 55 |  |  | 450 | 550 | 500 | 500+ | 160 |  | Transition 50' before to 50' past Wolfcamp. Focus on WOB and RPM parameters
7105-10000' | Wolfcamp - TD |  | 30 | 40 | 35 | 50 | 60 | 55 | 450 | 550 | 500 | 500+ | 160
During all Transitions highlighted in red, enable the ROP set point to ROP Target. Remove the WOB set points through the transition zones so it doesn't limit ROP.
On all formations, except the transitions, remove ROP set point on auto driller (or set to 400 so it doesn’t limit WOB). In these non-control drill intervals use WOB set points.
[15 empty] | 6.35 | 0

## Contacts
Waddell TR 3 #3813 Contact List
Savanna #417
Well Site Contacts
Personnel |  | Contact | Phone
Toolpusher
Toolpusher
Rig Supervisor (Day) |  | Clint Valentine | 337-380-8846
Rig Supervisor (Day) |  | Bryan Stringer | 337-257-3279
Rig Supervisor (Night)
Rig Supervisor (Night)
Vendor Contacts
Services | Company/Person | Location | Phone | Line
Hospital/Emergency | Ward Memorial Hospital | 406 S. Gary Ave Monahans, X 79756 | 911 432-943-6703 | Emergency Office
Sheriff | Ward County Sherriff's Office | 300 East 4th Monahans, TX 79756 | 432-943-6703 | Office
Sheriff | Crane County Sheriff's Office | 201 W 6th St, Crane, TX 79731 | 432-558-3571 | Office
Mud Loggers | Geo-site | Midland, TX | 325-655-4356 | Mobile
EDR (Electronic Drilling Recorder) | Pason | Midland, TX | 806-281-8370 | Mobile
All Casing | Patriot Threading | Midland, TX | 281-222-3936 903-235-3985 | Mobile
5-1/2" Production Casing (minimum 2 day notice) | Tubular Synergy Group | Midland, TX | 432-559-4742 | Cell
Bits | Cap Rock | Midland, TX | 432-230-0440 | mobile
Bits (Production Hole) | Halliburton - Jeff Hardin | Midland, TX | 903-780-5127 | mobile
Bits | Hughes | Odessa, TX | 432-230-6973 | mobile
Bits | NOV | Odessa, TX | 432-288-5150 | cell
Bits | Smith | Odessa, TX | 432-688-3340 | mobile
Bits | Halliburton | Midland, TX | 432-770-0208 | Office
Bits | Varel | Odessa, TX | 432-367-1658 | Tail: 230 sx (175% ex)
Bits (Surface Hole) | Ulterra | Midland, TX | 432-770-3287 | mobile
Survey Tools | Trueshot | Midland, TX | 972-505-0433 | Mobile
Motor | Baker | Midland, TX | 432-559-6313 | Mobile
Motor | Baker | Midland | 432-254-6703 | cell
Brine Water | Best of Brine | Monahans, Tx | 432-631-2317 | Mobile
Fresh Water (Well) | Kenny Bradford | Midland, TX | 432-813-7985 | Mobile
Casing Crews / LD | Bid out:
Casing Inspection Services | Bid out:
Cementing Services | Basic Energy Services | Midland, TX | 432-687-1994 | Dispatch
Cementing Services | Pro-Petro | Midland, TX | 432-425-4881 | Mobile
Centralizers | Innovex | Midland, TX | 432-250-9652 | Office
Welder | Double A Welding | Monahans, Tx | 432-208-5244 | Mobile
DC Inspection | Bid Out
Diesel | Blue Streak | Midland, TX | 432-262-1515 | mobile
Diesel | Pilot Thomas | Midland, TX | 432-813-6643 | Mobile
Diesel | Pilot | Midland, TX | 432-813-6643 | mobile
Directional (MWD, Motor, IBS) | Wellbenders | Midland, TX | 210-643-2960 832-493-1844 | cell(s)
Dirt Contractor/ Pit lining | Ian Barry | Midland, TX | 713-248-4672 | Mobile | Survey at <500' intervals after the Salado
Downhole Rentals | Alliance | Midland, TX | 307-789-0212 | office
Downhole Rentals | Triumph | Odessa, TX | 432-704-5130 | office
Downhole Rentals | Spidle Turbeco | Odessa, TX | 432-561-9495 | office
DP Corrosion | Savanna/Corrosion LTD |  |  | Office Mobile
Drilling Mud | Horizon Mud | Midland, TX | 432-425-0684 | Mobile
Drill Pipe (Rental) | Quail Tools | Midland, TX | 432-366-1419 | Office
Float Equipment | Antelope Oil Tool | Midland, TX | 432-250-1844 | office |  | 6.35 | #VALUE!
Float Equipment | Summit | Midland, TX | 877-860-0969 | office
Float Equipment | Innovex | Midland, TX | 432-250-9652 | Office
Gyro | Renegade (Jay Young) | Andrews, TX | 432-638-9793 | cell
H2S Safety Equipment | American Safety Services | Artesia, NM | 575-746-1096 | office
H2S Safety Equipment | Total Safety Solution | Midland, TX | 432 -557-0627 | cell
H2S Safety Equipment | Total Safety Solution | Midland, TX | 432 -557-0627 | Mobile
Pit Lining / Water Line | Ian Barry | Midland, TX | 713-248-4672 | Mobile
Rotating Head | Cutter Drilling Systems | Midland, TX | 432-631-4605 | Office
Conductor/ Anchors | Ian Barry | Midland, TX | 713-248-4672 | Mobile
Supplies & Thread Dope | Wilson Supply (DNOW) | Odessa, TX | 432-337-3541 | Office
Survey Tool | Ranger / Wenzel | Midland, TX | 432-848-3977 | cell
Survey Tool | Teledrift | Odessa, TX | 432-385-4188 | cell
Texas RRC | District 8 & 8A | Midland, TX | 432-684-5581 432-684-6005 | Office
Trailer House/ Porta-potties-Trash | Oil Patch | Midland, TX | 512-968-4422 | Dispatch
Fishing Tool | WFR | Midland, TX | 575-631-4075 | Mobile
Wellhead Equipment | Basin Pump Down | Midland, TX | 432-250-2003 | Mobile
Office Contacts
BBO Personnel | Contact | Cell # | Office # | Email
Drilling Advisor | Gus Yanez | 903-245-3079 |  | gyanez@blackbeardoperating.com
Asset Engineer | Kevin Foro | 303-884-2407 |  | kforo@blackbeardoperating.com
Asset Engineer | Paiten Tinar | 210-2157976 |  | ptinar@blackbeardoperating.com
Asset Engineer | Kevin Foro | 303-884-2407 |  | kforo@blackbeardoperating.com
Permian VP Operations | Ian Smith | 432-528-9628 |  | Ismith@blackbeardoperating.com
Field Foreman | Kenny Bradford | 432-813-7985 | 432-557-1470 | kbradford@blackbeardoperating.com
Asst Foreman | Dimas Porras | 432-438-5486 |  | dporras@blackbeardoperating.com
Pumper | Ryan Beal | 432-305- 6054 |  | rbeal@blackbeardoperating.com
Pumper | John Ashbrook | 432-631-7749 |  | jashbrook@blackbeardoperating.com

## Prog
General Drilling Procedure
Waddell TR 3 #3813 Drilling Procedure
This program contains the guiding procedures to be followed in the development of this property. It is meant only as a guide under normal-predicted conditions during the drilling operation of this well. As actual conditions differ from predicted, the Drilling Foreman on location, representing Blackbeard Operating, LLC will take appropriate actions needed to continue the drilling operation in the safest and most economical method possible. All changes will be reported to the drilling/operations engineer as soon as drilling operations allow. Please read COVID-19 protocol below. The comments, procedures, methods and equipment designs within this document are proprietary to Blackbeard Operating, LLC. Any use of said materials and procedures without authorization from Blackbeard Operating, LLC is prohibited.
Surface Hole
Prep Location
1 |  | Preview location prior to rig mobilization to confirm that dimensions meet operational needs, the conductor is set, and the rat hole and mouse hole are drilled.
2 |  | Read all permits and regulatory paperwork carefully to ensure all regulatory requirements are satisfied.
3 |  | Notify RRC 24 hours prior to spudding, running casing, and cementing. Note the date, time, person contacted, and job # on the daily report.
4 |  | Tubular requirement notifications should be made to pipe vendor in a timely fashion (minimum 2 days notice). Clean, drift, visually inspect, and tally all casing on location.
Drill & Survey Surface Hole
5 | a. | PU 17-1/2" surface bit and BHA per the Technical Data sheet (unless otherwise instructed by the Midland Office). Drill out with fresh water. Must run floats in BHA per TRRC. Take inclination survey within 500' from surface (all surveys thereafter 500'-1000'). If inclination exceeds 2.5°, back off weight and bring back towards vertical. (Increase the number of surveys to 1 per 300' if inclination exceeds 2.5° resume 1 per 500' when inclination is under 2.0°.)
| c. | Maintain mud properties per Technical Data Sheet. Circulate inner reserve pit and allow native mud to build funnel vis to ~32-34s. Only go into steel pits if necessary to control losses.
| d | Mix 2 sx paper per 100' drilled. From slug pit, pump ~10 bbls of high visc sweep every 100'-200' drilled. Circulate and pump paper sweeps, as necessary, before connections to ensure hole is clean and avoid packoffs.
6 | a. | Drill to match casing strap. Do not set casing more than 200’ below the protected depth specified in the TCEQ Water Board Letter unless an approved Application for Alternate Surface Casing Program is attached.
| b. | Circulate through steel pits and add 20 sx starch to <10cc water loss 300' before TD.
7 | a. | At TD circulate hole clean.
| b. | TOH at an even and steady pace. The Redbeds in this field can swell and become very tight. If this happens, pull very slow and steady till pipe becomes free again. Use surface jars if necessary. Do not pull more than DC weight.
Run Surface Casing
8 |  | Run 1 joint between the Texas pattern guide shoe and the float collar. Thread lock all connections from the guide shoe to the top of the float collar. Use Bestolife 2000 thread compound (or equivalent) on the remaining connections. Be certain not to use any thread compound containing lead or zinc.
9 |  | Install centralizers as specified on Technical Data Sheet.
10 |  | Ensure a casing swage is on the floor to wash down casing as necessary. Keep casing as full as possible to help maintain weight. If you cannot wash casing down, call Superintendent to discuss forward plan. If casing becomes stuck, be prepared to run 1” pipe down annulus to wash away bridge.
11 |  | Tag bottom and pick up two feet, circulate one to two casing volumes at max loss-free rate.
Cement Surface Casing
12 |  | Ensure cementing company has analyzed water samples for cementing.
13 |  | Pump 20 bbl FW ahead of cement. Pump cement slurry as defined in the Technical Data sheet. Catch wet and dry samples throughout job, sending dry samples to Midland if a problem arises. Plan to circulate cement to surface.
14 |  | Displace with FW. Bump the plug with 500 psi over final displacement pressure and hold for +/- 5 minutes. DO NOT OVERDISPLACE. Bleed off pressure and check float equipment. Send a copy or ensure that cementer sends a copy of pressure chart from job to Midland Office for well file.
15 |  | If cement does not circulate to surface, notify the RRC; prepare for a temp survey and 1" top out job.
NU WH & BOP
16 |  | Install 13-3/8" SOW x 13-5/8" 3M casing head, weld inside & outside, test void to 500 psi for a minimum of 5 min.
17 |  | Install BOP stack consisting of a drilling spool with choke and kill lines, double rams with pipe rams on top and blind rams on bottom, and an annular preventer with room for a rotating head on top. Should room not be available for the drilling spool, tie choke and kill lines to side outlets below blind rams.
18 |  | Test blind rams, manifold, and valves to Low 250psi & High 1,500psi prior to drilling out. Test manifold first & use a test plug if WOC time has not been reached (6hrs for Tail 500psi UCS). Keep a copy of test chart in well file for reference throughout the well. Inspect accumulator unit to ensure that precharge pressures and oil levels are within API specifications. Record tests and inspections on the IADC tour report. Line up for hard shut-in (Choke and first valve downstream of choke in closed position).
19 |  | WOC for a total of 6 hrs before testing casing (500 psi for tail UCS). Prior to drilling out, pressure test the casing to 1000 psig / 30 min per TRRC. If more than 10% pressure is lost during test, call Midland Office for plan forward. Keep a copy of test chart in well file for reference throughout the well. Do not drill out until after 9:05hrs passed since plug bumped (100 psi for lead UCS).
Intermediate Hole
Drill Intermediate Hole
1 |  | R/U a rotating head and H2S risk mitigation package.
2 | a. | No FIT test required IF all of the following requirements are met: 1) CMT to surface 2) Wet samples set up 3) Hard CMT in shoe 4) Compressive strength wait time is met. Contact office to discuss as needed.
| b. | Test annular and pipe rams to 250psi low and high 1500psi (positive test). Record tests and inspections on the IADC tour report and BBO drilling report. Drill out with brine water.
| c. | Drill out with a 12-1/4" bit and BHA per the Technical Data sheet (unless otherwise instructed by the Midland Office). Drill out with brine water (take sample of brine water from trucks and have mud engineer test chloride level and list on report). Must run floats in BHA per TRRC. Run inclination only survey tool in BHA & take survey 200' out from casing.
| d. | When drilling with a motor, differential pressure should be (200-500 psi).
| e. | Operate pipe rams daily and blind rams on trips.
3 |  | Follow parameter sheet while drilling through the Queen (historical deviation hits around 2,400'). After the Queen, run surveys not to exceed 500' intervals for the entire well. If inclination exceeds 2.5° below surface casing, back off weight and bring back towards vertical.
4 |  | Losses are not expected, but use fibrous materials as needed to control seepage and/or lost circulation. Pump viscous sweeps as needed for hole cleaning. Only add MF-55 to flowline (trickle); DO NOT add in DP. Prefered LCM make up: 20 sx Cotton seed hulls coarse + 10 sx cedar fiber + 20 sx Salt Gel + 5 sx starch for a 70 bbl sweep.
5 |  | Watch for differential sticking at ALL TIMES. Keep rotary turning or pipe moving as much as possible. On connections pick up off the slips & move the string before bringing the pump up to speed. If you get stuck don't overpull, work the string down and attempt to rotate to get loose
6 |  | If a flow is encountered note depth and amount of flow on daily report. Oil shows and water flows have been seen in offsets. Can have high H2S concentrations with water flows.
7 |  | Contact Midland Office if tripping is required and/or if ROP drops significantly for an extended time.
8 |  | Add starch to drilling mud 300' from TD according to Tech Data sheet if hole is sticky.
9 |  | Monitor losses, flow, and pressures encountered in the San Andres Interval. Report back to engineering with details.
10 |  | At section TD of 3,700' - circulate hole clean & take final survey. POOH LD DP. Monitor pits to see if well is flowing and kill as necessary.
| b. | If the well is flowing at TD or while tripping DP, notify Midland office for decision to log well. Kill well prior to logging.
| c. | If total vertical section as calculated from the inclination surveys is greater than the distance from the nearest lease line, discuss with Engineer whether we need to run a gyro at TD.
Run Intermediate casing
11 |  | Notify RRC 24 hours prior to running and cementing casing.
12 |  | Run 1 joint between the float shoe and the float collar. Thread lock all connections from float shoe to top of float collar. Use Bestolife 2000 thread compound (or equivalent) on the remaining connections. Be certain not to use any thread compound containing lead.
13 |  | Ensure a casing swage is on the floor to wash down casing as necessary.
14 |  | Install centralizers as specified on Technical Data Sheet.
15 |  | Run marker joints as specified on the Well Sketch.
16 |  | Tag bottom, pick up two feet. Circulate the hole and RU cementing head. Circulate the hole a minimum of one full circulation at max loss-free rate.
Cement Intermediate Casing
17 |  | Ensure cementing company has analyzed water samples for cementing.
18 |  | Pump 20 bbls FW pre-flush. If open hole logs are taken, ensure there is at least 35% excess cement volume for the open hole. Pump prog if the 35% is met. Note: if adjusting cement volumes based on caliper log ensure 2 independent calculations are performed prior to modifying volumes. Contact Midland for any changes. Pump cement slurry as defined in the Technical Data sheet if caliper log is not available. Catch wet and dry samples throughout job, sending dry samples to Midland if a problem arises. Plan to circulate cement to surface.
19 |  | Displace with fresh water. Note on daily report how much cement circulates. We are not required to circulate cement on this intermediate string. On wells with no CMT to surface, report 200' TOC per Prog.
20 |  | Bump plug with 500 psi over final displacement pressure. DO NOT OVERDISPLACE. Release pressure and ensure float equipment is holding. Send a copy or ensure that cementer sends a copy of pressure chart from each stage to Midland Office for the well file.
21 |  | If any flow is observed after cement job, wash out BOPs and close in on well for 6 hours minimum.
NU WH & BOP
22 |  | ND BOP, Set slips, Install 13-5/8" 3M x 11" 3M casing head, weld inside & outside, test void to 1,500 psi for a minimum of 15 min.
23 |  | Install BOP stack consisting of a drilling spool with choke and kill lines, double rams with pipe rams on top and blind rams on bottom, and an annular preventer with room for a rotating head on top. Should room not be available for the drilling spool, tie choke and kill lines to side outlets below blind rams.
24 |  | Test blind rams, manifold, and valves to Low 250 psi & High 1,500 psi prior to drilling out. Test manifold first & use a test plug if WOC time has not been reached (6hrs for Tail 500psi UCS). Keep a copy of test chart in well file for reference throughout the well. Inspect accumulator unit to ensure that precharge pressures and oil levels are within API specifications. Record tests and inspections on the IADC tour report. Line up for hard shut-in (Choke and first valve downstream of choke in closed position).
25 |  | WOC for a total of 6 hrs before testing casing (500 psi for tail UCS). Prior to drilling out, pressure test the casing to 1500 psig / 30 min per TRRC. If more than 10% pressure is lost during test, call Midland Office for plan forward. Keep a copy of test chart in well file for reference throughout the well. Do not drill out until after 9:05hrs passed since plug bumped (100 psi for lead UCS).
Production Hole
Drill Production Hole
1 |  | R/U a rotating head and H2S risk mitigation package.
2 | a. | No FIT test required IF all of the following requirements are met: 1) CMT to surface 2) Wet samples set up 3) Hard CMT in shoe 4) Compressive strength wait time is met. Contact office to discuss as needed.
| b. | Test annular and pipe rams to 250 psi low and high 1500 psi (positive test). Record tests and inspections on the IADC tour report and BBO drilling report. Drill out with brine water.
| c. | Drill out with a 7-7/8" bit and BHA per the Technical Data sheet (unless otherwise instructed by the Midland Office). Drill out with brine water (take sample of brine water from trucks and have mud engineer test chloride level and list on report). Must run floats in BHA per TRRC. Run inclination only survey tool in BHA & take survey 200' out from casing.
| d. | When drilling with a motor, differential pressure should be (200-500 psi).
| e. | Operate pipe rams daily and blind rams on trips.
3 |  | If inclination exceeds 2.5° below Intermediate casing, back off weight and bring back towards vertical.
4 |  | Losses are not expected, but use fibrous materials as needed to control seepage and/or lost circulation. Pump viscous sweeps as needed for hole cleaning. Only add MF-55 to flowline (trickle); DO NOT add in DP. Prefered LCM make up: 20Sx Cotton seed hulls coarse + 10 Sx cedar fiber + 20 Sx Salt Gel + 5 Sx starch for a 70 bbl sweep.
5 |  | Watch for differential sticking at ALL TIMES. Keep rotary turning or pipe moving as much as possible. On connections pick up off the slips & move the string before bringing the pump up to speed. If you get stuck don't overpull, work the string down and attempt to rotate to get loose
6 |  | If a flow is encountered note depth and amount of flow on daily report. Oil shows and water flows have been seen in offsets. Can have high H2S concentrations with water flows.
7 |  | Contact Midland Office if tripping is required and/or if ROP drops significantly for an extended time.
8 |  | Add starch to drilling mud 300' from TD according to Tech Data sheet if hole is sticky.
9 |  | Monitor losses, flow, and pressures encountered. Report back to engineering with details.
10 |  | At Hole TD circulate hole clean & take final survey. POOH LD DP. Monitor pits to see if well is flowing and kill as necessary.
| b. | If the well is flowing at TD or while tripping DP, notify Midland office for decision to log well. Kill well prior to logging.
| c. | If total vertical section as calculated from the inclination surveys is greater than the distance from the nearest lease line, discuss with Engineer whether we need to run a gyro at TD.
Run Production Casing
11 |  | Notify RRC 24 hours prior to running and cementing casing.
12 |  | Run 1 joint between the float shoe and the float collar. Thread lock all connections from float shoe to top of float collar. Use Bestolife 2000 thread compound (or equivalent) on the remaining connections. Be certain not to use any thread compound containing lead.
13 |  | Ensure a casing swage is on the floor to wash down casing as necessary.
14 |  | Install centralizers as specified on Technical Data Sheet.
15 |  | Run marker joints as specified on the Well Sketch.
16 |  | Tag bottom, pick up two feet. Circulate the hole and RU cementing head. Circulate the hole a minimum of one full circulation at max loss-free rate.
Cement Production Casing
17 |  | Ensure cementing company has analyzed water samples for cementing.
18 |  | Pump 20 bbls FW pre-flush. If open hole logs are taken, ensure there is at least 35% excess cement volume for the open hole. Pump prog if the 35% is met. Note: if adjusting cement volumes based on caliper log ensure 2 independent calculations are performed prior to modifying volumes. Contact Midland for any changes. Pump cement slurry as defined in the Technical Data sheet if caliper log is not available. Catch wet and dry samples throughout job, sending dry samples to Midland if a problem arises. Plan to circulate cement to surface.
19 |  | Displace with fresh water. Note on daily report how much cement circulates. We are not required to circulate cement on this production string. On wells with no CMT to surface, report 200' TOC per Prog.
20 |  | Bump plug with 500 psi over final displacement pressure. DO NOT OVERDISPLACE. Release pressure and ensure float equipment is holding. Send a copy or ensure that cementer sends a copy of pressure chart from each stage to Midland Office for the well file.
21 |  | If any flow is observed after cement job, wash out BOPs and close in on well for 6 hours minimum.
ND BOP & NU WH, RDMO
22 |  | ND BOP, set slips, Install 11" 3M x 7-1/16" 5M tubing head, weld inside & outside, test tubing head to 1,500 psi for a minimum of 15 min.
23 |  | Jet and clean the pits, release rig.
Loss Remediation Procedure
1 |  | Upon drilling into a loss zone evaluate the severity of the losses. If offset information indicates there will be losses have a LCM pill premixed before drilling into lose zone. Drill 100ft into loss zone and attempt to heal with the following sweep. 40bbl LCM Sweep: 10Sx of Cotton seed hulls (Coarse) 5Sx of Cedar Fiber (Coarse) 10 Sacks of Salt Gel 5 Sacks of Starch
2 |  | Monitor returns post LCM sweep. If partial returns are seen proceed to work with mud engineer to come up with a game plan to sweep the hole as we drill to try and heal our losses. If we still have full losses and we know of severe losses in offset well than we will plan to cement out losses.
3 |  | Dry drill an additional 300-500ft before coming out of hole to cmt. While coming out of the hole stop 100ft above the loss zone and pump a heavy LCM sweep as follows. 70 bbls LCM Sweep: 20 Sx of cotton seed hulls (coarse) 10 Sacks of Cedar fiber (coarse) 20 sacks of salt gel 5 sacks of starch
4 |  | POOH and LD BHA and Drill collars.
5 |  | RBIH w/ open ended drill pipe. Before exiting surface casing shoe (conductor shoe if cmting surface hole) plan on attempting to establish returns. Continue to RIH w drill pipe and stop ~100ft above loss zone. Rig up cementers and plan on pumping CMT
| a | Discuss CMT program with engineering. Previous success has been made with a full truck load of CMT ~280 sx of a Class C CMT at 14.2ppg. Discuss with cementers before pumping.
| b | Establish an injection rate before pumping cement.
| c. | Mix and pump cmt paying close attention to annular pressure and lift pressure on pump trucks. Displace Cmt into formation. • If you notice lift pressure or annular pressure while cementing. Cut Cmt and go to flush. Flush 2 annular volumes of FW and prepare to POOH to previous CSG shoe. IF deemed necessary mix and pump another annular volume of FW at shoe before pulling DP out of hole. • If lift pressure remains constant than displace cmt and flush with 2 annular volumes of FW. POOH W/ DP.
6 |  | Let CMT sit for 8 hours before RIH w/ bit to drill out cmt.
7 |  | After 8 hours tag top of plug and note on report. If top of CMT plug feels very “soft” than considering shutting in an additional 4 hours to allow CMT to harden.
COVID-19 Preventative Measures
1 |  | Everyone entering a Blackbeard drilling location must check in with either the company man or the tool pusher.
| a | The Savanna tool-pusher will be accountable for all the Savanna employees.
| b | The Company man will be accountable for everyone else.
2 |  | Everyone entering location must be wearing a mask prior to checking in with the company man or tool pusher.
3 |  | Everyone must sanitize their hands prior to signing in.
4 |  | Company man or tool pusher will be required to take the temperature of the person signing in.
| a | In the event they test over 100 Degrees F they will either be sent home or allowed to try again after cooling in their own personal space (most likely their vehicle) .
| b | If they are below the 100 Degree F threshold than they can sign in and go about their business.
5 |  | Company man and tool pusher will sanitize their office area/sign in area throughout the day.
6 |  | When/if possible, work 6ft apart from one another.
7 |  | A mask will be required when a person must work at a distance of 6ft or less with any other individual.
| a | Most of the people working on location can work 6ft apart from each other.
| b | Designed for events where multiple people will be working in close proximity.
| c | Will be enforced on pre-spud or JSA meetings.

## Geo-Prog
Geologic Prognosis - Vertical Well | [5 empty] | CX3818
WELL NAME: | Waddell TR 3 #3813 |  |  | FIELD OR PROSPECT: |  | University Waddell (Devonian) |  |  |  | Comments:
SURFACE LOCATION: | 2010' FSL, 650' FWL, Sec 22, Blk B-25, Crane, TX
API Number: | 42-103-36784 |  | RRC Permit Number: |  |  | 868552 |  | Drilling Rig: | Savanna #417
Driving Directions: | SEE ATTACHED MAP FOR DIRECTIONS
LAT/LON (NAD83): | 31.546657, -102.490691 |  |  |  | KB: |  |  | 2777
LAT/LON (NAD27): | 31.546521, -102.490269 |  |  |  | GROUND ELEVATION: |  |  | 2765
PRIMARY OBJECTIVES: |  | Wolfcamp |  |  | PROPOSED TOTAL DEPTH: |  |  | 10000
SECONDARY OBJECTIVES: |  | Glorieta/Clearfork
KNOWN DRILLING HAZARDS: |  | Rustler Anhydrite, possible lost circulation. Yates, possible water flow. See depths below.
OPEN-HOLE LOGGING PROGRAM: |  | None
RECOMMENDED CORING AND TESTING PROGRAM: |  |  |  | None
WELLSITE SUPERVISION: |  | Bryan Stringer Cell: 337-257-3279 -or- Clint Valentine Cell: 337-380-8846
MUD LOGGER: |  | Geo-site Cell: 325-655-4356 *Start 2 man mud logging after drilling out of surface casing
GEOLOGIST: |  | Rene Wiksveen 432-230-7629, rwiksveen@blackbeardoperating.com
ESTIMATED GEOLOGIC TOPS
| SUBJECT WELL |  |  | PRIMARY CORRELATION WELLS (NAME, LOC.):
| EST. KB: | 12 |  | Waddell WN #272 (1,300' E) |  | Waddell WN #708 (1,870' SE)
| ELEV_KB: | 2777 |  | ELEV_KB: | 2695 | ELEV_KB: | 2689
FORMATION | DEPTH | SS |  | DEPTH | SS | DEPTH | SS |  | COMMENTS
GAU | 450 | 2327 |  | 450 | 2245 | 450 | 2239 |  | Water board Letter
SWR 13 Excptn Letter | 900 | 1877 |  | 900 | 1795 | 900 | 1789 |  | Possible lost circulation
Yates | 2278.7 | 498.3 |  | 2155 | 540 | 2150 | 539
Queen | 3056.3 | -279.3 |  | 2907 | -212 | 2901 | -212
San Andres | 3515.8 | -738.8 |  | 3412 | -717 | 3407 | -718 |  | Possible water flow
** Glorieta | 4550.2 | -1773.2 |  | 4458 | -1763 | 4414 | -1725 |  | Dolomite
** Upper Clearfork | 5042.7 | -2265.7 |  | 4860 | -2165 | 4807 | -2118 |  | Dolomite
Tubb | 5362.3 | -2585.3 |  | 5178 | -2483 | 5138 | -2449 |  | Dolomite
** Lower Clearfork | 5422.3 | -2645.3 |  | 5237 | -2542 | 5181 | -2492 |  | Dolomite
Wichita-Albany | 6047.3 | -3270.3 |  | 5868 | -3173 | 5855 | -3166 |  | Limestone/Dolomite
* Wolfcamp | 7053 | -4276 |  | 6861 | -4166 | 6826 | -4137 |  | Limestone/Dolomite
Wolfcamp Base | 7317 | -4540 |  | 7127 | -4432 | 7109 | -4420 |  | Limestone/Dolomite
Perm Detrital | 7634.4 | -4857.4 |  | 7434 | -4739 | 7399 | -4710 |  | Limestone/Shale
Cisco | 7840.1 | -5063.1 |  | 7575 | -4880 | 7543 | -4854 |  | Limestone
Canyon | 7903.4 | -5126.4 |  | 7626 | -4931 | 7609 | -4920 |  | Limestone
Strawn | 8038.9 | -5261.9 |  | 7717 | -5022 | 7755 | -5066 |  | Limestone/Shale
Atoka | 8396 | -5619 |  | 8071 | -5376 | 7872 | -5183 |  | Shale
Barnett | 8609 | -5832 |  | 8284 | -5589 | 8232 | -5543 |  | Shale
Miss Lime | 8880 | -6103 |  | 8555 | -5860 | 8510 | -5821 |  | Limestone/Shale
Woodford | 8902 | -6125 |  | 8577 | -5882 | 8522 | -5833 |  | Shale
Devonian | 9119 | -6342 |  | 8764 | -6069 | 8714 | -6025 |  | Limestone
Total Depth | 10000 | -7223 |  | 9500 | -6805 | 9280 | -6591
* Primary Objective
** Secondary Objective
Production Casing Cement - Volumes to be adjusted according to fluid caliper logs, along with actual casing depths. Plan top of tail cement at 3,500’.
MUDLOGGING REQUIREMENTS
Interval: | BSC to TD, sample every 30', keep dry samples
Gas Readings: | Begin 2-man mud logging over shakers after drilling out of surface casing
If gas readings are not consistent with offset wells, please perform necessary equipment testing and calibration
Reporting: | Email geologist when you arrive onsite
Send one Daily PDF Report covering the last 24 hours with your morning email update
Send email update at least 4 times daily ( 5 & 11 AM/PM ). Include 1"/5" PDFs, 5" TIFF, LAS in every update
Notify Geologist immediately if there are any mechanical or technical issues call/text/email
Annotation | Please annotate presence/lack of FLU and CUT on the mudlog; including oil in cuttings/pit/etc
Please annotate any mechanical issues affecting the gas/cuttings data collection on the mudlog
Images: | Send images of cuttings (hourly chart), cuttings trays, and cut per well
Datum: | NAD27
Final Logs: | Send final digital log email to distribution list
Send 2x Color prints to Kyle Schoener, 200 N. Loraine, Ste 300, Midland, TX 79701
Cuttings: | Send cuttings to Midland Subsurface Library

## Target Well Data (hidden)
Vertical - Fullerton | [13 empty] | Weight Factor
Recent Wells | [5 empty] | Other |  |  |  | Well | Spud | Est Surf ROP | 160 | 78% | 1700 | Suface TD
FCU #8020 | 2016-05-05 | [10 empty] | Est Prod ROP | 98.5 | 77% | 7350 | Production TD
FCU #8020 (Record, 5/16) |  | (1/-100) |  | (1/-100) |  | (1/-100) |  | (1/-100) |  | Current |  | Target 6.1 days
Days | Depth | Days | Depth | Days | Depth | Days | Depth | Days | Depth | Days | Depth | Days | Cum Days | Depth | Description
0 | 53 | [10 empty] | 0 | 0 | 53 | spud
0.041667 | 53 | [10 empty] | 0.25 | 0.25 | 800 | drill
0.41667 | 1669 | [10 empty] | 0.30048 | 0.55048 | 1700 | TD surf | 0.55048
0.4375 | 1705 | [10 empty] | 1.15 | 1.7005 | 1700 | TD surf to drill Prod
0.45833 | 1705 | [10 empty] | 1 | 2.7005 | 3520 | drill
0.52083 | 1705 | [10 empty] | 1 | 3.7005 | 5340 | drill
0.54167 | 1705 | [10 empty] | 1 | 4.7005 | 7160 | drill
0.8125 | 1705 | [10 empty] | 0.10438 | 4.8049 | 7350 | TD prod | 3.1044
0.84375 | 1705 | [10 empty] | 0.7 | 5.5049 | 7350 | TOH log
0.92708 | 1705 | [10 empty] | 0.6 | 6.1049 | 7350 | Csg / Cmt | 1.3
1.0625 | 1705
1.1667 | 1705
1.2083 | 1705
1.2292 | 1705
1.3125 | 1705
1.3438 | 1705
1.3854 | 1705
1.3958 | 1705
1.4167 | 1705
1.4479 | 1705
1.4896 | 1705
1.8438 | 2903
1.8646 | 2903
2.4167 | 4262
2.8646 | 5365
2.8854 | 5365
3.4167 | 6438
3.6562 | 6848
3.6667 | 6848
4.0625 | 7403
4.1042 | 7403
4.2917 | 7403
4.3958 | 7403
4.4167 | 7403
4.6458 | 7403
4.8646 | 7403
4.9062 | 7403
5.0312 | 7403
5.0938 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403
5.1562 | 7403

## Wellhead (hidden)
8-5/8” x 5-1/2” Wellhead Assembly
8-5/8”
5-1/2”
11” 3M
7”-1/16 5M
2”5M
2” 5M
45”
17”
22”
6”
8-5/8” x 11”3M SOW CSGHD, 11”3M x 7”5M TBGHD w 2” LPO and ball valves, 7”5M x 2-3/8” EUE TBGHDADPT